## Tasks
Title | Status | Priority | Start date | Due date | Assigned to | Labels | Checklist items
Signed contract and first invoice | Done |  | 2026-09-28 | 2026-09-28 | Account manager | Admin
Welcome email and kickoff invite | Done |  | 2026-09-28 | 2026-09-28 | Account manager | Client
Collect access (analytics, CMS, ad accounts) | Waiting on client | high | 2026-09-29 | 2026-10-03 | Client | Client | [x] Google Analytics; CMS login; Ad accounts
Kickoff workshop | In progress |  | 2026-10-01 | 2026-10-01 | Strategist | Strategy
Audit and 90-day plan | To do |  | 2026-10-02 | 2026-10-08 | Strategist | Strategy
Quick wins (first two weeks) | To do |  | 2026-10-06 | 2026-10-12 | Specialist | Delivery
First monthly report | To do |  | 2026-10-17 | 2026-10-18 | Account manager | Delivery
Check-in call | To do |  | 2026-10-18 | 2026-10-18 | Account manager | Client