## Tasks
Title | Status | Priority | Start date | Due date | Assigned to | Labels | Checklist items
Define goals, budget and date | Done |  | 2026-09-28 | 2026-09-30 | Event lead | Budget
Book the venue | Done | high | 2026-10-01 | 2026-10-07 | Event lead | Venue | [x] Shortlist 3 venues; [x] Site visits; [x] Sign the contract
Confirm speakers | In progress |  | 2026-10-05 | 2026-10-18 | Program manager | Speakers | [x] Invite list; Confirm 5 speakers; Collect bios and photos
Catering and AV quotes | In progress |  | 2026-10-10 | 2026-10-16 | Logistics | Logistics; Budget
Registration page and tickets | To do |  | 2026-10-14 | 2026-10-17 | Marketing | Promotion
Promotion plan (email and social) | To do |  | 2026-10-18 | 2026-11-11 | Marketing | Promotion
Travel and accommodation for speakers | To do |  | 2026-10-28 | 2026-11-03 | Logistics | Logistics; Speakers
Run of show and staffing | To do | high | 2026-11-12 | 2026-11-16 | Event lead | Logistics
Event day | To do | urgent | 2026-11-26 | 2026-11-26 | Everyone
Thank-you email and feedback survey | To do |  | 2026-11-27 | 2026-11-28 | Marketing | Promotion