## Tasks
Title | Status | Priority | Start date | Due date | Assigned to | Labels | Checklist items
Campaign brief and target audience | Done |  | 2026-09-28 | 2026-09-29 | Marketing lead |  | [x] Objective and KPIs; [x] Persona; [x] Budget split
Key message and offer | Done |  | 2026-09-30 | 2026-10-01 | Marketing lead | Content
Landing page copy | In progress |  | 2026-10-02 | 2026-10-05 | Copywriter | Content
Creative assets (ads, banners, visuals) | In progress | high | 2026-10-03 | 2026-10-08 | Designer | Design
Email sequence (3 emails) | To do |  | 2026-10-07 | 2026-10-10 | Copywriter | Email
Social media calendar | To do |  | 2026-10-07 | 2026-10-09 | Social media manager | Social
Paid ads setup | To do | high | 2026-10-11 | 2026-10-13 | Ads specialist | Paid ads | Audiences; Budgets and bids; Tracking pixels
Launch day | To do | urgent | 2026-10-14 | 2026-10-14 | Marketing lead
Mid-campaign optimization | Ideas |  | 2026-10-21 | 2026-10-22 | Ads specialist | Paid ads
Results report and learnings | Ideas |  | 2026-10-31 | 2026-11-01 | Marketing lead