## Tasks
Title | Status | Priority | Start date | Due date | Assigned to | Labels | Checklist items
Sprint planning | Done |  | 2026-09-28 | 2026-09-28 | Product owner
User login with magic link | In progress | high | 2026-09-29 | 2026-10-03 | Dev A | Feature | [x] API endpoint; Email template; Rate limiting; Tests
Fix: export fails on Safari | In review | urgent | 2026-09-30 | 2026-10-02 | Dev B | Bug
Onboarding checklist UI | In progress |  | 2026-09-30 | 2026-10-05 | Designer | Design; Feature
Upgrade dependencies | To do |  | 2026-10-03 | 2026-10-04 | Dev B | Tech debt
Search results pagination | To do |  | 2026-10-04 | 2026-10-07 | Dev A | Feature
Fix: wrong time zone on due dates | To do | high | 2026-10-05 | 2026-10-06 | Dev B | Bug
QA regression pass | To do |  | 2026-10-08 | 2026-10-09 | QA tester
Sprint review and demo | To do |  | 2026-10-11 | 2026-10-11 | Product owner
Retrospective | Backlog |  | 2026-10-11 | 2026-10-11 | Scrum master