## Tasks
Title | Status | Priority | Start date | Due date | Assigned to | Labels | Checklist items
Plans and budget approved | Done |  | 2026-09-28 | 2026-09-30 | Owner
Building permit | Done |  | 2026-09-30 | 2026-10-04 | Contractor | Permits
Demolition and site prep | In progress |  | 2026-10-04 | 2026-10-08 | Contractor | Structural
Framing and structural work | To do | high | 2026-10-09 | 2026-10-16 | Contractor | Structural
Rough-in electrical | To do |  | 2026-10-17 | 2026-10-20 | Electrician | Electrical
Rough-in plumbing | To do |  | 2026-10-17 | 2026-10-20 | Plumber | Plumbing
Rough-in inspection | Inspection | urgent | 2026-10-22 | 2026-10-22 | Inspector | Permits
Drywall and insulation | To do |  | 2026-10-23 | 2026-10-28 | Contractor
Flooring, paint and fixtures | To do |  | 2026-10-29 | 2026-11-09 | Contractor | Finishes
Final inspection | To do | high | 2026-11-11 | 2026-11-11 | Inspector | Permits
Punch list and handover | To do |  | 2026-11-13 | 2026-11-17 | Contractor | Finishes | Walkthrough with owner; Fix snags; Final clean; Keys and warranties