## Tasks
Title | Status | Priority | Start date | Due date | Assigned to | Labels | Checklist items
Pick the topic and confirm with the teacher | Done |  | 2026-09-28 | 2026-09-29 | Everyone | Admin
Split roles and set deadlines | Done |  | 2026-09-29 | 2026-09-29 | Everyone | Admin
Literature research | Doing |  | 2026-09-30 | 2026-10-06 | Sam | Research | [x] Find 10 sources; Write summaries; Bibliography
Survey and data collection | Doing |  | 2026-10-01 | 2026-10-08 | Lee | Research
Draft report sections | To do | high | 2026-10-08 | 2026-10-15 | Everyone | Writing
Edit and merge the report | To do |  | 2026-10-16 | 2026-10-19 | Alex | Writing
Presentation slides | To do |  | 2026-10-17 | 2026-10-20 | Jordan | Slides
Rehearsal | To do |  | 2026-10-22 | 2026-10-22 | Everyone | Slides
Submit the report and present | To do | urgent | 2026-10-25 | 2026-10-25 | Everyone