## Tasks
Title | Status | Priority | Start date | Due date | Assigned to | Labels | Checklist items
Kickoff meeting and project goals | Done |  | 2026-09-28 | 2026-09-28 | Project manager |  | [x] Agree on KPIs; [x] Confirm budget; [x] Share the timeline
Sitemap and page inventory | Done |  | 2026-09-29 | 2026-10-01 | Project manager | Content
Wireframes for key pages | Done |  | 2026-10-01 | 2026-10-05 | Designer | Design
Visual design and style guide | In review | high | 2026-10-05 | 2026-10-10 | Designer | Design
Write homepage and landing page copy | In progress |  | 2026-10-06 | 2026-10-12 | Copywriter | Content
Build page templates | In progress | high | 2026-10-10 | 2026-10-19 | Developer | Development
On-page SEO and redirect plan | To do |  | 2026-10-16 | 2026-10-19 | SEO lead | SEO | Map old URLs to new URLs; Titles and meta descriptions; XML sitemap
Analytics and conversion tracking | To do |  | 2026-10-22 | 2026-10-23 | Developer | Development
Cross-browser and mobile QA | To do | high | 2026-10-25 | 2026-10-29 | QA tester | QA | Chrome, Safari, Firefox; iOS and Android; Forms and checkout
Performance and Core Web Vitals pass | Backlog |  | 2026-10-28 | 2026-10-30 | Developer | Development; SEO
Go-live and DNS switch | To do | urgent | 2026-11-03 | 2026-11-03 | Project manager
Post-launch monitoring | Backlog |  | 2026-11-04 | 2026-11-08 | SEO lead | SEO